## Slide 1
Dieses Veranstaltung wurde durch den Asyl-, Migrations- und Integrationsfond (AMIF) der Europäischen Union mitfinanziert. Der Inhalt gibt ausschließlich die Meinung der EMV-LII-Projektpartnerschaft wieder und liegt in deren alleiniger Verantwortung. Die Europäische Kommission übernimmt keine Verantwortung für die Verwendung der darin enthaltenen Informationen.
Training Module: Project Management

## Slide 2
Training Objectives
Obtain an overview of methods of project development
Gain a deeper understanding of project management
Learn about practical tools and methods
Dieses Veranstaltung wurde durch den Asyl-, Migrations- und Integrationsfond (AMIF) der Europäischen Union mitfinanziert. Der Inhalt gibt ausschließlich die Meinung der EMV-LII-Projektpartnerschaft wieder und liegt in deren alleiniger Verantwortung. Die Europäische Kommission übernimmt keine Verantwortung für die Verwendung der darin enthaltenen Informationen.

## Slide 3
Introduction and Check-In
Hi, my name is …..
When it comes to project management, we are particularly interested in …..
When you finished this training, what would you like to take with you?

## Slide 4
Agenda
Project development: turning your idea into a project
How do I write a project proposal?
Project Management

## Slide 5
Project Development: Turning Your Idea Into a Project

## Slide 6
What is a project?
A project is characterised by:
Complexity
A clearly defined goal
Limited Resources
Singularity
Innovation
Limitation of Time
1. Project Development

## Slide 7
    Situation analysis—Problem description
    Target group(s)
    Effects
    Indicators
    Project activities and achievements
    Sustainability
    Cost and financing/expenditure and income plan
1. Project Development
A project application reflects the planning process and is guided by the following questions:
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 8
1. Stakeholder Analysis
2. Problem Analysis
3. Strategic Analysis
4. Effect Analysis
5. Definition of Indicators
1. Project Development
Possible Steps in the Planning Process:
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 9
    Identify individuals, groups, governmental and non-governmental institutions, companies, etc. that may be affected by the project.
    The stakeholders are all related to the project—affected or involved, directly or indirectly, positively or negatively.
1. Project Development
Stakeholder Analysis

## Slide 10
    provides better insight into the existing situation and
    the influence of the social environment on those involved;
    is based on the knowledge and viewpoints of those involved;
    is sometimes based on the creation of a problem tree, which has emerged during participatory workshops and captures and maps the respective priorities of the stakeholders.
1. Project Development
Problem Analysis

## Slide 11
Strategic Analysis
    Analysing alternative solutions that could contribute to the achievement of the objective;
    Evaluating the respective merits of the approaches;
    Selecting the best strategy based on criteria. These are agreed upon by the representatives of the stakeholders directly involved.
1. Project Development
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 12
Urgency of the situation
Relevance for the targeted group
Social aspects
Existing knowledge and possibilities (in regard to the targeted group)
Existing financial resources and expertise etc.
Complementarity to other projects
Adds to present challenges or contributes to decreasing inequality (e.g. gender equality)
Relevancy for partner countries, the EU or other international entities
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html
1. Project Development
Effect Analysis
Possible criteria:

## Slide 13
Effect Analysis
Effects are changes in a state as a result of an intervention.
They can be endogenous and non-endogenous, expected or unexpected, positive or negative.
They occur from the first moment of the intervention, during the entire project duration and in very different areas.
Effects are the result of social interactions.
1. Project Development
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 14
Indicators are parameters that have been selected to illustrate a specific, often not directly measurable and complex issue.
They say what a change can be observed or measured by (yardsticks).
Quantitative indicators with a performance value:
  XY percent of those trained have found a job
Qualitative indicators with a performance value:
  XY say they have found a better job
1. Project Development
Definition of Indicators
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 15
What information should an indicator contain?
Subject reference: Who? (e.g. target group)
Spatial reference: Where? (e.g. region)
Time reference: When/ how long?
Quantity: How much/ how many?
Quality: How good/ which criterion is changing?
1. Project Development
Definition of Indicators
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 16
Definition of Indicators
Indicators must be SMART:
Timely: timely, useful in a reasonable time for project management.
Relevant: important for what they are supposed to measure and in relation to the project logic (type of indicator);
Available: available from existing source;
Measurable: measurable with reasonable effort;
Specific: specific in terms of quality and quantity;
1. Project Development
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 17
Definition of Indicators: Ways to develop indicators
1. Measure or count
Exact numbers
Example: count participants, indicate number of participants
2. Scale
Gradable description
Example: Scale the frequency of diseases: always - often - sometimes - rarely - never
3. Classify
Non-gradable characteristics
Example: YES or NO: “Do you have the right to vote in your country of residence?"
4. Describe qualitatively
Exemplary description in words only
Example: : simply describe in words what is important in the context of this indicator: "A group of women from neighbourhood X in M. have started baking doughnuts from soy flour to sell in neighbourhood Y".
1. Project Development
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 18
How to Write a Project Proposal

## Slide 19
Requirements of a project proposal
Funding requirements are met
Submitted on time
Complete application (current forms used?)
All questions have been answered
Guidelines have been followed
The Application is clear, concise and comprehensible
The Application is based on facts
The Application logic is respected (e.g.: no description of project activities when it is about problem analysis)
Cost plan reflects project activities
A good project proposal is a prerequisite for the approval of a project. However, a good project proposal does not guarantee a good project.
2. How to write a project proposal
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 20
Dos and Don’ts in the writing of a project proposal: Do
Include essential contents, methods and didactic concepts or include them as examples. Do so even if things are not always fixed and can change.
Follow the "logical" structure of an application, without "telling" and repeating the project idea. Be careful not to write about objectives and methods in the problem analysis part.
Follow the structure and do not describe the measures in epic breadth when describing the targeted group!
Focus on the project goal but do not make the mistake of describing too many and very different goals that are unrealistic!
2. How to write a project proposal
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 21
...assume that donors or people who decide on projects know the association, the work and the concrete projects. Remember to describe your organisation and the project in a comprehensible way.
...put items, products or entire activities in the cost plan that are not even described or mentioned in the application. Especially with the sometimes quite useful documentation of the project, it is assumed that this does not need to be explained further.
Dos and Don’ts in the writing of a project proposal: Don’t
2. How to write a project proposal
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 22
Project Management

## Slide 23
Project Phases
Start
First project draft
Planning
Detailed project draft
Implementation
Review
Stakeholder analysis
Needs analysis
Impact orientation
Monitoring
Controlling
Evaluation
Completion
3. Project Management
Source: https://www.vamos-akademie.de/wp-content/uploads/2021/03/Arbeitsblatt_Detaillierte-Projektplanung.pdf

## Slide 24
A good project: content criteria - project implementation
    Transparency of funding flows and project planning
    Monitoring and accompanying evaluation
    Compliance with procurement rules
    Personnel: recruitment/payment/gender/respect for workers' rights
    Flexibility: adapting project strategy if conditions change
    Evaluation
    Internal evaluation
    External evaluation
    Analysis of the evaluation results
    Lessons learned
    The Basis for further projects
Content criteria - Evaluation
3. Project Management
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 25
Meaningful and successful project management...
consists of three phases/components: planning, implementation and evaluation;
sees planning as a participatory process of shared understanding and agreement;
focuses equally on impact and process;
consists of defined phases;
is open in terms of methods and tools; and
includes cyclical feedback loops throughout the process.
3. Project Management
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 26
3. Project Management
Cost items
Cost plan: contains all costs including administrative costs
The cost plan should reflect the measures applied for
explain larger cost items in the application text
Composition/amount of costs should be recognisable.
> if possible defined in units (e.g. 10 teaching units 90 min. á 100 € = 1.000,00 €)
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 27
Accounting
Should be considered from the beginning!
Consists of content and financial accounting.
3. Project Management
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 28
Situation description/problem description
Target groups
Effects/project objectives
Indicators (qualitative and quantitative)
Description and explanation of project activities
Cross-cutting issues
Sustainability
Cost and financing plan
Final evaluation (conclusion, consequences)
3. Project Management
Case Report
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 29
Simple/complete proof of use
Consists of voucher list, cost plan, financing plan (detailed overview of all expenses and income of the project).
Accounting by project/cost centre (personnel costs, fees, travel costs, accommodation/food, material costs, administrative costs)
No payment without receipt
Observe time limits (budget year)
Check donors for economic efficiency, proportionality and plausibility
3. Project Management
Financial Report
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 30
Last confirmed cost and financing plan in debit
with reduced project costs:
Cost estimates must be available upon request (public procurement law: from 500 €-1,000 €, comprehensible price calculation with three companies, from 1,000 €, three written offers) (Example Germany).
3. Project Management
Target/ Actual Comparison of Costs
    Administrative costs decrease in percentage terms
    Funding amount decreases in percentage
    Enclose receipts (depending on the funding agency) - Reconciliation/reference to receipts in the progress report
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 31
    Charged costs must reflect the content of the project.
    Check whether all costs are eligible (travel expenses abroad)
    Verifiable fee scales must be taken into account (BAköV rates).
    Justify deviations of >20% and apply for reclassification/approval with financial statement.
    Adjust Cofinancing in time if third-party funds are not approved
    Totals of cost and financing plan must match.
    Settle accounts on time or apply for extension in time.
3. Project Management
More Tips
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 32
    All funds available to the NGO (not earmarked for projects approved by other donors)
    Project-related donations are regarded as external funds by individual donors.
    Donations, sponsorship income, reserves from association assets.
    Revenues from the implementation of the project generally to be used to finance the project, e.g. entrance fees, sales proceeds, participant contributions.
Equality Capital
3. Project Management
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html

## Slide 33
Show the value of voluntary work contributions from third parties free of charge (e.g. infrastructure such as technical equipment, meeting rooms and/or e.g. accommodation and catering).
Can sometimes be counted as own resources (see funding guidelines for each country/budget line).
Source: https://www.nord-sued-bruecken.de/foerderung/foerderprogramme/in-sdg.html
3. Project Management
Valorised Services
Valorisation of services = valorisation of labour services without real cash flow